# Technical Appendix — ZK Proofs on Soroban: Recovery + Privacy Bundle

Companion to SDF_PROPOSAL_ONE_PAGER.md. This is for the SDF protocol team and any reviewer who wants the architecture, milestones, risks, and references in full.

## 1. Executive recap

We are proposing a single coordinated grant that lands two ZK applications on Stellar, with hard contractual track separation:

- Pillar 1 — g2c: ZK account recovery as a universal primitive. A BIP-39 seed-derived owner_secret is committed on-chain at enrollment as Poseidon2(owner_secret). On recovery, a Noir/UltraHonk proof bound to a fully-specified auth_hash triggers a 30-day time-locked key rotation through a new g2c-recovery-controller contract. During the timelock window the WebAuthn signer is forbidden from removing the ZK signer; cancellation requires both WebAuthn and a fresh proof of seed-knowledge, with a hard cap of 2 cancels per recovery initiation.

- Pillar 2 — neftwerk: ZK privacy as a sector validator. Three Noir circuits (arts1_mint, arts1_ownership, arts1_recovery) implement "private title, public provenance" for the ARTS-1 token standard, with the recovery circuit being the same primitive as Pillar 1.

Framing: Universal primitive in g2c + sector application in neftwerk. The shared substrate is Noir + UltraHonk + Poseidon2 + BN254 + Soroban 25.x, and we estimate ~30–40% engineering shared across the two tracks — concentrated in substrate work (verifier crate, browser SDK, Poseidon2 instantiation, audit RFP, OZ shim) rather than co-developed circuit/contract code. The per-FTE loading chart in §8 reflects this: tracks are largely time-sliced across people, with the substrate items shared once at the boundary. Track A and Track B funds are disbursed independently; an A0 benchmark failure or a Pillar 2 compliance-gate slip does not affect Track A.

## 2. Shared ZK substrate

| Layer | Choice | Notes |
| --- | --- | --- |
| Circuit DSL | Noir (nargo 1.0.0-beta.x) | Mature tooling; first-class UltraHonk backend |
| Proving system | UltraHonk via Aztec's Barretenberg (bb 0.87.x) — pinned by SHA-256 of the release tarball | Universal SRS; A2 VK registry supports bb-version bumps |
| Hash | Poseidon2 over BN254 scalar field, Aztec parameter set t=3 (commit width-2 sponge), round constants pinned by SHA-256 | Domain-separated per use (commitment / recovery / mint / ownership / nullifier) |
| Curve | BN254 | ~100-bit pairing security; migration plan to BLS12-381 (Appendix A) |
| ECDSA-P256 gadget | noir-bigcurve + noir_ecdsa from noir-lang, pinned commit + matched bb 0.87.x compatibility | A1 spec names exact tags |
| Verifier | ultrahonk-soroban-verifier Rust crate (no_std + alloc) | Deployed to Stellar testnet today |
| OZ compatibility | New g2c-oz-compat shim crate (see §3) | Single re-export surface; storage-layout XDR hash regression suite in CI |
| Soroban SDK | 25.x | Pinned to a specific commit at A1 |
| Browser prover | bb.js (WASM, lazy-loaded on /recover/ only) | COOP/COEP deployment plan in §5 |

Why UltraHonk over Groth16, Plonk, Halo2, RISC0/SP1? Universal SRS removes per-circuit ceremonies — necessary for a recovery primitive instantiated against bespoke wallet circuits. A0 publishes a Groth16-on-Soroban verification-CPU comparison; if Groth16 verifies at <1/3 the budget for the fixed Pillar-1 recovery circuit, we add a Groth16 verifier behind the same VK registry (no fork of the substrate; same VK upgrade governance applies).

## 3. Architecture: ZK signer plug-in to g2c

The integration introduces three new contracts plus a compatibility shim:

- g2c-zk-recovery-verifier — stateless OZ Verifier. Implements the full trait: verify(env, hash, key_data, sig_data) -> bool, canonicalize_key(env, key_data) -> Bytes, batch_canonicalize_key(env, key_data_list) -> Bytes. KeyData = BytesN<32> (Poseidon2 commitment). SigData = (proof_bytes: Bytes, public_inputs: Vec<BytesN<32>>). Cross-invokes ultrahonk-soroban-verifier.

- g2c-recovery-controller — stateful contract owning the pending-rotation state machine (§4). Persistent storage with explicit TTL extension paid from a per-account recovery deposit; if deposit is exhausted, complete_recovery fails-closed and the pending state archives safely. Entrypoints: initiate_recovery, cancel_recovery, complete_recovery. Controller upgrades are governed by the same 3-of-5 VK multi-sig + 14-day timelock as the verifier registry.

- g2c-recovery-guard-policy — separate OZ Policy contract, scoped to ContextRuleType::CallContract(self_address) and installed on every ContextRule that can authorize signer mutations. Its enforce() reads the recovery-controller's pending-rotation state via cross-contract call; during a pending rotation it blocks remove_signer(zk) and requires both signers' auth for add_signer(*). The cross-contract-call gas overhead is measured explicitly in A0 (Policy-with-cross-call benchmark).

- g2c-oz-compat — thin re-export crate over the OZ stellar-accounts surface area g2c uses. Pins the OZ version (commit hash + storage-layout XDR hash). CI test fails on storage-layout drift. Future OZ upgrades touch this one file. A1 deliverable also publishes an OZ_UPSTREAM_DIFF.md documenting every divergence between g2c's consumer-side trait usage and upstream OZ traits, so the contract auditor can scope the shim's compatibility surface explicitly.

### No non-factory enrollment paths

ZK-signer registration is only supported via the atomic factory path (g2c-factory.create_account_with_zk_signer). No other enrollment path (manual SDK call, migration of existing g2c accounts, post-deployment registration) is supported. This forecloses pre-enrollment squatting on non-factory paths: a commitment cannot be registered against an account_id outside the atomic factory transaction. Migration of existing g2c accounts to ZK recovery is a separate post-grant deliverable with its own threat model.

### Sequence diagram for complete_recovery

Submitter        recovery-controller       SmartAccount         guard-policy        webauthn-verifier (existing)
   │                    │                       │                    │                    │
   │── complete_rec ───▶│                       │                    │                    │
   │                    │── verify (now ≥ initiation_ledger          │                    │
   │                    │   + timelock_duration + Σ cancel_pauses)   │                    │
   │                    │── verify deposit_rent_sufficient (else     │                    │
   │                    │   fail-closed; pending entry archives)     │                    │
   │                    │── verify proof valid ─│                    │                    │
   │                    │── verify cancel_count │                    │                    │
   │                    │   ≤ cap (=2)          │                    │                    │
   │                    │── inner call ────────▶│ add_signer(new_pk) │                    │
   │                    │                       │── __check_auth ───▶│                    │
   │                    │                       │   Context = CallContract(self,           │
   │                    │                       │              add_signer)                 │
   │                    │                       │   ContextRule = Default                  │
   │                    │                       │   guard-policy.enforce(ctx, signers, …) │
   │                    │                       │   reads pending_recovery_state           │
   │                    │                       │   sees: pending, controller is signer,   │
   │                    │                       │   timelock_expired, proof_verified       │
   │                    │                       │   → permits add_signer                  │
   │                    │                       │── inner call ─────│ require_auth(ctlr) │
   │                    │                       │── ok ─────────────│                    │
   │                    │   inner call ────────▶│ remove_signer(pk_old)                   │
   │                    │                       │── __check_auth ───▶│ same path → permits │
   │                    │── refund deposit ────▶│                    │                    │
   │                    │── emit RecoveryCompleted                                          │
   │── ok ──────────────│                                                                   │

The completion call is two inner calls (add_signer then remove_signer) gated by the same guard-policy invocation against the same pending-recovery state. A0 measures this exact path.

### Critical safety property: signer-removal guard

The existing OZ add_signer / remove_signer (smart-account/contract.rs:105–113) requires only current_contract_address().require_auth() — a stolen WebAuthn signer satisfies this. Naive integration is bypassable.

The fix is the g2c-recovery-guard-policy above. Three properties make it correct:

- The Policy is registered on every ContextRule that lists a signer with add_signer/remove_signer authority — not just the Default rule. A1 deliverable includes a per-rule policy-attachment audit.

- The Policy is scoped to ContextRuleType::CallContract(self_address), so it intercepts inner calls to the SmartAccount's signer mutation entrypoints regardless of how auth_contexts selects rules.

- The recovery-controller is registered as a Signer::Delegated(controller_addr), so complete_recovery() can satisfy current_contract_address().require_auth() when it cross-calls the SmartAccount to atomically rotate the signer — but only after timelock + proof-verified.

A4 acceptance criterion: differential tests cover (i) stolen-passkey-only bypass attempt, (ii) double-recovery, (iii) expiration race, (iv) cancellation during legitimate recovery, (v) policy-not-on-rule bypass, (vi) cancel-loop attack (see §4).

## 4. Recovery flow end-to-end (Pillar 1)

Six steps. (1)–(2) at SmartAccount enrollment; (3)–(6) on recovery.

- Seed at enrollment. During g2c onboarding the wallet asks the user to write down a BIP-39 mnemonic (passphrase optional, explicitly supported). The seed never touches the network.

- Commitment + recovery deposit on-chain. The wallet derives owner_secret = HKDF-SHA256(ikm = seed, salt = network_passphrase, info = "g2c-recovery-v1" ‖ account_id), reduces modulo BN254 scalar order, and submits commitment = Poseidon2(domain_sep_commitment, owner_secret) to the recovery-controller along with a one-time recovery deposit (covers ~40 days of TTL extension at current Soroban rent). The deposit is refundable on complete_recovery net of consumed rent.

- Recovery trigger. User has lost their passkey. Opens mysoroban.xyz/recover/. Cross-account discovery decision: the page does NOT maintain a server-side commitment → C-address index (privacy regression). Instead the user enters the C-address from a recovery card. Recovery-card content rule (security-critical): the recovery card contains only the C-address and a human-readable account label. The card MUST NOT contain the BIP-39 seed, which is held on a separate paper artifact never digitized as QR. This separation defeats the physical-card exfiltration attack (photo of QR ≠ access to seed). Wallets MUST provide a recovery-card export at enrollment as an A5 acceptance criterion. Re-enters BIP-39 mnemonic with wordlist autocomplete + checksum validation + passphrase prompt + language selection.

- Per-account recovery initiation rate limit: the controller enforces a maximum of 3 initiate_recovery calls per 90-day rolling window. This prevents recovery-deposit griefing (initiate→cancel→re-initiate). The 4th attempt within the window is rejected; the user must wait until the oldest initiation falls outside the window.

- Proof generation in the browser. bb.js (WASM, lazy-loaded) generates an UltraHonk proof for the circuit:

- public inputs:
  commitment           : Field    // pinned at enrollment
  auth_hash            : Field    // single Field, see preimage spec below
private inputs:
  owner_secret         : Field
  new_signer_pubkey    : (Field, Field, Field, Field, Field)  // 5 limbs ≤128 bits
asserts:
  Poseidon2(domain_sep_commitment, owner_secret) == commitment
  auth_hash == Poseidon2(domain_sep_recovery, account_id, network_passphrase, contract_addr,
                         limb0, limb1, limb2, limb3, limb4, nonce, timelock_duration)
  // Pubkey integrity:
  each_limb < 2^128                                // range check
  limbs_compose_canonically_to_65_bytes            // canonical decomposition
  point_on_secp256r1(decompressed_pubkey)          // on-curve check

- The auth_hash is exposed as a single Field (Poseidon2-hashed externally to one element). All subordinate fields enter the Poseidon2 input vector with explicit byte-encoding rules (Appendix A.1).

- On-chain submission. Wallet calls recovery-controller.initiate_recovery(account, proof, sig_data, new_pubkey). The controller:

  - Recomputes auth_hash from supplied fields and verifies match against the proof's public input

  - Verifies timelock_duration ≥ 7 days (controller-side floor; not just in-circuit)

  - Verifies nonce is monotonic (controller's per-account counter)

  - Pays TTL extension from the recovery deposit (35 days)

  - Stores pending rotation in persistent storage

  - Emits RecoveryInitiated(account, new_pubkey_hash, completes_at_ledger, cancel_count=0) event

  - Wallets MUST subscribe and notify via the user's opted-in channel (push/email/SMS)

- 30-day timelock + cancellation policy + completion. During the window, cancel_recovery() requires:

  - WebAuthn signer signature over cancel_hash = Poseidon2(domain_sep_cancel, account_id, contract_addr, current_recovery_nonce, ledger_seq_at_cancel)

  - AND a fresh cancel_proof: a mini-Noir circuit proving Poseidon2(domain_sep_commitment, secret) == commitment for the same commitment. This means cancellation requires either the legitimate user (who has the seed) or an attacker who has both the WebAuthn signer AND the seed (in which case rotation is the easier attack — cancellation is pointless).

  - Cap of 2 cancels per recovery initiation. A 3rd cancel_recovery is rejected; the recovery completes after the 30-day window. Cancel count is included in RecoveryInitiated/RecoveryCancelled events for monitoring.

  - 24h cooldown between consecutive cancels.

- After the timelock + total cancellation pauses, anyone may call complete_recovery(). The controller — registered as a Signer::Delegated admin signer — atomically calls SmartAccount.add_signer(new_pubkey) and SmartAccount.remove_signer(old_webauthn_signer) in a single inner call, gated by the g2c-recovery-guard-policy which now permits both because the controller's auth is valid post-timelock-post-proof.

The cancel-loop attack is closed by the cap + the cancel-proof requirement. The TTL-archival race is closed by the per-account deposit covering the full window.

## 5. Privacy flow end-to-end (Pillar 2)

Three circuits, with explicit input/output specs and gate-count estimates (to be confirmed at A0).

### arts1_mint (heaviest)

Verifies at minting that both Neftwerk (institutional co-signer) and the collector authorized the mint over the same auth_hash.

- Public inputs: commitment (output), provenance_root, auth_hash (single Field), mint_id, token_id.

- Private inputs: institutional ECDSA-P256 signature, collector ECDSA-P256 signature, provenance_secret, collector owner_secret, collector pubkey limbs.

- Asserts: institutional and collector pubkeys both on-curve; both ECDSA verify against auth_hash; canonical-limb encoding for both pubkeys; auth_hash binds mint_id, token_id, both pubkeys, provenance_secret, and an institution-side freshness counter; commitment = Poseidon2(domain_sep_arts1_mint, collector_pk_limbs, owner_secret).

- Estimated gates (Aztec-engineer estimate, to confirm at A0): 220–280k UltraHonk gates. Browser prove: 90–180s in WASM, peak heap 1.2–1.8 GB. Will OOM iOS Safari; mobile mint must use server-side proving via Neftwerk Protocol (acceptable trust model at mint because Neftwerk is the institutional co-signer anyway).

### arts1_ownership

- Public inputs: commitment, auth_hash, token_id.

- Private inputs: owner_secret, collector pubkey limbs, ECDSA signature over auth_hash.

- Asserts: auth_hash binds token_id, transaction nonce, contract address, function selector, call args; pubkey on-curve; canonical limbs; commitment matches; signature valid.

- Estimated gates: ~110k UltraHonk gates. Browser prove: 8–15s.

### arts1_recovery

- Public inputs: owner_secret_commitment, auth_hash, token_id, new_owner_pubkey_limbs.

- Private inputs: owner_secret.

- Asserts: auth_hash binds token_id, contract address, new_owner_pubkey_limbs, monotonic nonce, timelock floor; commitment matches.

- Estimated gates: 6–9k UltraHonk gates. Browser prove: 2–4s.

### Privacy properties and known gaps

The on-chain ARTS-1 contract knows what a token is (via metadata CID) but not its price or its collector. Price/split logic is off-chain in Neftwerk's database, injected at sale time as transaction arguments ("late-binding").

Known gap: an observer can infer the price by watching USDC outflows on settlement. Roadmap commitment: a fourth circuit arts1_settlement using the nullifier-set primitive of §6 (out of scope for this grant; explicitly named here as the next milestone).

## 6. Deployment evidence

### soroban-zk-demo — full E2E on testnet

- ./test_e2e.sh runs build → deploy → prove → verify on testnet.

- Three-contract pattern: zk-contract (commitment + cross-call), ultrahonk-soroban-contract (proof verifier), zk-factory-contract (factory).

- Note: the current on-disk circuit (circuits/ownership_proof/src/main.nr) is a hash-knowledge demo; the assert(new_commitment == new_commitment) no-op does not bind the public input. A0 deliverable #1 brings this into agreement with §4's spec before any other circuit work.

### rs-soroban-ultrahonk — verifier crate

- Soroban contract wrapping the UltraHonk verifier; integration tests for simple and Fibonacci-chain circuits.

- Cost-measurement script in scripts/invoke_ultrahonk/ for testnet gas readings.

- VK currently immutable at __constructor; A2 delivers the upgrade governance.

### Nullifier-set + Merkle-frontier primitive

- Reference implementation with depth-20 tree, insertion proofs, and nullifier-set state on Soroban.

- Demonstrates the substrate for revocation, replay protection, and future batched settlement (arts1_settlement).

- Repo directory will be renamed from tornado_classic to nullifier_set_primitive before grant kickoff.

## 7. Milestone breakdown

Two parallel tracks plus a shared pre-grant benchmark. All milestones have measurable acceptance criteria; tranche release is gated on each milestone's acceptance.

### Pre-A0 — Mandatory pre-disbursement skeleton (no SDF fee)

Hard precondition for ANY SDF disbursement, including A0. Before grant signing, the team publishes the arts1_mint_skeleton.nr gate count under bb 0.87.x — two noir-bigcurve ECDSA-P256 verifies + dummy Poseidon2, no real binding. ~2 days of work, performed at the team's own cost. The published number replaces the v3 estimate as the reference for A0's pass criterion. No SDF money flows until this is published.

### A0 — Pre-grant Soroban gas benchmark (weeks 1–2, $30k split 50/50)

Cash-flow: A0 is reimbursement after delivery, not advance funding. The team carries A0 work at risk; SDF disburses A0a's $15k on A0a deliverables verified, A0b's $15k on A0b deliverables verified. If A0 fails the pass criterion, the $30k is not paid; no clawback because no advance was made.

A0 deliverables, paid 50/50 on completion:

| Half | Amount | Deliverables |
| --- | --- | --- |
| A0a | $15k | (1) On-disk ownership_proof circuit brought into spec agreement. (2) Published CPU instructions, memory bytes, and resource fee for verify_proof on testnet for: simple-1-input, Fibonacci-chain, and the arts1_mint-shaped reference circuit (using the pre-A0 skeleton). (3) Policy-with-cross-contract-call benchmark (the g2c-recovery-guard-policy + controller cross-call cost). |
| A0b | $15k | (1) Groth16-on-Soroban verifier comparison for the recovery circuit. (2) Browser proving benchmarks (peak heap, prove time, WASM bundle size) on three named device tiers: iPhone 14, Pixel 7, 2020 MacBook Air. (3) Mobile-prove feasibility report for arts1_mint (expected: server-side mint required). |

Pass criterion (calibrated against pre-A0 skeleton number, not vapor): arts1_mint-shaped circuit verification cost on Soroban must satisfy BOTH:

- Design assumption check: cost ≤ 1.5 × measured_skeleton_cost (the 1.5× multiplier accommodates the gap between skeleton with dummy Poseidon2 and the full circuit with real binding/provenance work)

- Operational headroom check: cost ≤ 80M instructions (= 80% of Soroban's 100M-instruction cap; leaves 20M for auth, storage, and policy cross-call overhead under load)

AND Policy-with-cross-call adds <10M instructions overhead per __check_auth. Pass = both bounds met.

If the actual arts1_mint cost exceeds either bound, SDF and team decide between (a) descope, (b) re-architect with recursive aggregation, (c) terminate. If pre-A0 skeleton itself measures above 50M instructions, the 1.5× bound exceeds 75M which collides with the 80M ceiling — Track B's arts1_mint is descoped to single-ECDSA in scope before any funds are committed.

### Track A — g2c ZK recovery ($150k tranched 10/20/30/40)

| # | Milestone | Weeks | Acceptance criteria |
| --- | --- | --- | --- |
| Tranche-payment milestones are bolded. Other milestones are unpaid prerequisites whose work is rolled into the next paid tranche's release. |  |  |  |

| A1 (10% — $15k) | Spec doc + Noir circuits (recovery + cancel-proof) | 2–4 | Single PDF pinning: Poseidon2 round constants by SHA-256; noir-bigcurve and noir_ecdsa commit hashes pinned; limb canonicalization rules + on-curve check spec; auth_hash byte-encoding; HKDF parameters; field-reduction rule; cancellation-hash spec; security argument (reduction sketch); replay matrix (account / network / contract / nonce / token / encoding). Recovery + cancel-proof circuits compile; replay/cross-account/cross-network/canonical-encoding unit tests pass. g2c-oz-compat shim crate published with storage-layout XDR hash regression suite in CI; OZ_UPSTREAM_DIFF.md published documenting all consumer-side divergences. Verifier trait fully implemented (verify, canonicalize_key, batch_canonicalize_key); canonicalize_key malleability fuzzer in tests. pnpm test:parity CI test running round-trip across bb.js prover, JS Poseidon2 commitment generator, and Soroban verifier; covers all 7 domain separators with adversarial vectors (cross-implementation drift kills recovery silently). OZ stellar-accounts commit pinned. | | A2 (20% — $30k) | Verifier crate v2 + VK governance + recovery-controller + recovery-guard-policy | 4–7 | ultrahonk-soroban-verifier v2 with VK registry (circuit_id → VK). VK governance: 3-of-5 multi-sig with diversified-quorum rule across three groups: Group A (Stellar-aligned): 1 SDF + 1 Stellar Foundation external (independently selected; treated as a single effective vote for collusion analysis). Group B (auditing org): 1 OpenZeppelin. Group C (community): 2 signers via a two-stage public RFP (open nomination → 30-day public comment → on-chain attestation by Group A + Group B). Quorum rule: any 3-of-5 quorum MUST include at least 1 signer from Group A AND at least 1 signer from {B ∪ C}. This forecloses both an all-Stellar quorum (Stellar-only collusion impossible — Group B or C must consent) AND an all-non-Stellar quorum (OZ + community alone cannot push a VK upgrade). All keys FIDO2 + WebAuthn attestation required, with accepted AAGUIDs published (YubiKey 5 series, SoloKeys, T-series; HSM-only operation). 180-day mandatory key rotation verified on-chain. Kill-switch with anti-DoS: any 1-of-5 can pause a pending upgrade for 7 days; a second pause within 30 days requires 4-of-5 to overcome (prevents one compromised signer from indefinitely DoS'ing emergency rotation). 14-day timelock on upgrades, opt-in per account, orphan-token migration ceremony documented. g2c-recovery-controller deployed to testnet with full state machine + state-machine PDF + storage-layout diagram + concrete Context example for complete_recovery per §3 sequence diagram. g2c-recovery-guard-policy deployed; per-rule attachment audit produced. Controller upgrade governance: same multi-sig + same diversified-quorum rule + same timelock + same opt-in. | | A3 | Atomic enrollment-time registration | 6–7 | g2c-factory create_account accepts pre-registered ZK signer at construction with Vec<Signer>, atomically registers commitment with recovery-controller, and enforces timelock_duration ≥ 7 days on enrollment. Unpaid; rolled into A4. | | A4 (30% — $45k) | SmartAccount integration + signer-removal guard + cancel-loop differential tests | 7–9 | OZ Policy correctly scoped to CallContract(self_addr) and installed on every signer-mutating ContextRule. Differential tests covering: stolen-passkey bypass, double-recovery, expiration, cancellation, policy-not-on-rule bypass, cancel-loop, TTL-archival race, restore-after-cancel ordering. | | A5 | Browser proving UX + recovery-card export | 8–10 | <5 min recovery proof on 2020 MacBook Air, <8 min on Pixel 7 (median across 3 devices of each tier). BIP-39 wordlist autocomplete, checksum, passphrase, language selection. Recovery-card export at enrollment (printable C-address QR; seed remains on separate paper). Cross-origin isolation deployment plan validated. Graduated unlock during timelock (read-only access). Unpaid; rolled into A6. | | A6 (40% — $60k, with $15k withhold if integrator agreement not signed) | Audit-ready freeze + mainnet launch + integrator signed | 10–14 | All contracts and circuits frozen for 4 weeks circuit audit + 3 weeks contract audit + 2-week fix window each. Mainnet deployment with at least one external wallet integrator's signed integration agreement. Fallback (no schedule slip): if signed agreement is not secured by week 12, A6 ships with (a) integrator's-guide published + (b) public integration RFP open + (c) ≥1 LOI in hand; SDF holds back $15k of the $60k tranche pending signed agreement within 60 days post-grant, releasing the withhold on signature. |

### Track B — neftwerk ZK privacy ($200k tranched 10/20/30/40)

Pillar 2 funding gated on Pillar 2 compliance gates (§11) AND A0 pass. B1 disbursement held until C1 legal opinions are in SDF's hands.

Tranche-payment milestones are bolded. Other milestones are unpaid prerequisites whose work is rolled into the next paid tranche's release.

| # | Milestone | Weeks | Acceptance criteria |
| --- | --- | --- | --- |
| B0 | Coinflow ↔ Soroban transaction-attachment spike + dual-ECDSA feasibility | 2–3 | Coinflow ↔ Soroban primary-sale flow validated on testnet. Dual-ECDSA constraint count published (real circuit, not skeleton). Unpaid; rolled into B1. |
| B1 (10% — $20k) | Three-circuit spec | 3–5 | Spec PDF following A1 format. All three circuits compile. C1 legal opinions delivered to SDF reviewer as gate condition. |
| B2 | arts1_ownership | 5–7 | Compiled circuit + verifier integration; replay tests pass; on-curve + canonical-limb tests pass. Unpaid; rolled into B4. |
| B3 | arts1_recovery (parameterized A1 primitive) | 7–8 | Same Noir circuit pattern as A1, parameterized for token_id. Unpaid; rolled into B4. |
| B4 (20% — $40k) | arts1_mint | 7–10 | Compiled circuit; verification cost within A0 budget; descope to single-ECDSA collector signature if A0 left <2× headroom (decision documented); server-side proving infrastructure for mobile mint live. |
| B5 | Browser pipeline + royalty enforcement scaffolding | 10–12 | Royalty-locked secondary-transfer logic compiles on testnet. Unpaid; rolled into B6. |
| B6 (30% — $60k) | ARTS-1 token contract + on-chain freeze | 10–13 | E2E mint and transfer with privacy on testnet. Royalty-locked secondary transfers as acceptance criterion. C2 on-chain freeze function for legal process implemented and tested. |
| B7a (40% — $80k less $5k withhold if mainnet) | ARTS-1 pilot launch (mainnet or testnet) | 13–14 | Conditional on signed MoU at A0 completion. Acceptance: pilot transaction(s) executed on mainnet (or fully-rigged testnet pilot ready for partner activation if MoU not secured by week 6) + telemetry instrumentation live + 7-day in-grant retention metric (not 30-day, which exceeds grant period). |
| B7b (post-grant — $0 delta or released $5k withhold) | 30-day retention report | week 17–18 | Disbursed conditionally after grant close: telemetry already running, report generation only. SDF releases the $5k withhold from B7a on receipt of B7b (only applicable if mainnet pilot launched at B7a). |

### Shared dependencies

- A2 deliverables feed B2/B4/B5.

- Browser proving SDK (A5) is consumed by B6.

- Audit firms cover both tracks (see §8).

## 8. Budget

Total: $380k over 14 weeks.

| Line item | Amount | Tranching |
| --- | --- | --- |
| A0 — pre-grant benchmark (split 50/50) | $30k | A0a $15k / A0b $15k on completion of each half |
| Track A — g2c ZK recovery | $150k | 10% / 20% / 30% / 40% on A1 / A2 / A4 / A6 |
| Track B — neftwerk ZK privacy | $200k | 10% / 20% / 30% / 40% on B1 / B4 / B6 / B7a (B7b is post-grant, $0 delta with $5k withhold from B7a if mainnet launched), gated on A0 pass + Pillar 2 compliance gates; B1 held until C1 in SDF reviewer's hands |
| Total | $380k |  |

Audit credits requested separately from SDF's standard pool. Two auditors, two scopes:

- Circuit audit (4-week scope): zkSecurity, Veridise, or Spearbit ZK practice. Scope: all four Noir circuits + cancel-proof circuit, Poseidon2 parameter set, ECDSA-in-circuit gadgets, limb canonicalization, on-curve checks, replay protection, auth_hash preimage binding.

- Contract audit (3-week scope): OtterSec, Trail of Bits, or Halborn. Scope: g2c-zk-recovery-verifier, g2c-recovery-controller, g2c-recovery-guard-policy, g2c-oz-compat shim, generalized factory changes, ARTS-1 token contract.

2-week fix window after each audit. No mainnet deployment until both audits clean.

Team: 3 FTE — one ZK/circuit lead (Aztec/Noir background required, must have shipped a production ECDSA-in-circuit gadget), one Soroban/Rust contracts engineer, one frontend/browser-prover engineer. Names and FTE percentages provided to SDF on grant signing. Per-FTE loading chart (delivered with grant agreement, summary here):

| Week | ZK lead (Track-A bias) | Contracts eng (cross-track) | Frontend/prover eng |
| --- | --- | --- | --- |
| 1–2 | A0 skeleton + measurements | A0 Policy benchmark + cost script | A0 browser benchmarks |
| 3–4 | A1 spec PDF + circuits | A1 OZ shim + verifier trait | A1 parity CI test scaffold |
| 5–7 | B1 / B2 spec + circuit | A2 controller + guard-policy + VK registry | A5 wireframes + recovery-card export |
| 7–9 | B4 mint circuit | A3 factory + A4 integration tests | A5 BIP-39 UX + WASM lazy-load |
| 9–11 | B5 / B6 circuits + parity tests | B6 token contract + freeze function | A5 final UX + cross-origin isolation |
| 11–13 | Audit-prep freeze + circuit-audit interface | Audit-prep freeze + contract-audit interface | A5 mainnet polish |
| 13–14 | B7 pilot launch support | A6 mainnet deploy + integrator handoff | B7 telemetry + retention metrics |

Budget transparency: $380k = $30k (A0, partial allocation across 3 FTE for 2 weeks) + $350k for the 12-week Track A + Track B build (≈ $9.7k/FTE/week × 3 FTE × 12 weeks). The 14-week envelope includes A0; A0's $30k is sized as partial-allocation pre-grant work, not a full 3-FTE × 2-week sprint. All figures are gross (fully loaded comp, taxes, benefits, overhead); team commitments are documented at grant signing. SDF retains the right to descope or restructure if the loading chart proves untenable at week 4 review.

Track independence clause (codified in grant agreement): Track A milestone payments are not contingent on Track B status, and vice versa, except for the A0 prerequisite. Track A continues even if Track B is paused for compliance, A0 fails for arts1_mint-sized circuits, or B7's MoU does not materialize. Track B is held back if Track A's audit invalidates the shared verifier.

Compliance reviewer designation: SDF designates a named internal counsel or external reviewer for Pillar 2 compliance gates C1/C3 (legal opinions). Reviewer name disclosed at grant signing. No tranche release without reviewer sign-off.

## 9. Risk and mitigation table

| # | Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- | --- |
| 1 | UltraHonk gas/budget exceeds 100M-instruction cap for arts1_mint | Medium | High | A0 measurement gate paid as flat pre-grant fee; pre-built arts1_mint_skeleton.nr published before A0 signs; failure paths defined (descope / aggregate / terminate). |
| 2 | Larger circuits (~50+ constraints, dual-ECDSA) untested | Medium | Medium | A0 includes arts1_mint-shaped reference; B0 runs real dual-ECDSA spike; B4 has explicit single-ECDSA descope path. |
| 3 | Recovery proof front-running or replay across accounts/networks/contracts/encodings | Medium | High | auth_hash preimage fully specified §4; on-curve + canonical-limb checks added; replay matrix in A1 covers six vectors. |
| 4 | WebAuthn signer evicts ZK signer (stolen-passkey bypass) | Medium | Critical | g2c-recovery-guard-policy scoped to CallContract(self_addr), installed on every signer-mutating ContextRule; differential tests in A4. |
| 5 | VK governance attack (malicious VK swap) | Low | Catastrophic | 3-of-5 multi-sig with named organizational signers (1 SDF + 1 Stellar Foundation external + 1 OZ + 2 community via public RFP); FIDO2 hardware attestation required; 14-day on-chain timelock; opt-in per account; 180-day mandatory rotation; kill-switch (any 1-of-5 pauses); existing accounts pinned to enrolled VK at the verifier-crate level. |
| 6 | Browser proving fails on mobile or under cross-origin isolation | Medium | Medium | A5 publishes measured numbers; WASM lazy-loaded only on /recover/; COOP/COEP headers + Cloudflare Worker compatibility validated. arts1_mint mobile mint uses server-side proving via Neftwerk Protocol (institutional co-signer is online anyway). |
| 7 | No audit yet | Certain | High | Two named audit firms (circuit + contract), 4+3 weeks separate scopes, 2-week fix window each, no mainnet without clean reports. |
| 8 | Pillar 2 securities/AML/sanctions exposure | Medium | High | Track B funds gated on §11 compliance gates; SDF reviewer designated; B1 held until C1 in hand. Track A independent. |
| 9 | BN254 ~100-bit pairing security degrades within RWA token lifespan | Low | High | Migration plan in Appendix A; VK registry supports parallel BLS12-381 verifier. |
| 10 | OZ stellar-accounts library upgrades break pending recoveries | Medium | Medium | g2c-oz-compat shim crate; storage-layout XDR hash CI regression test; library pinned at A1. |
| 11 | Cancel-loop attack — stolen passkey blocks legitimate recovery indefinitely | Medium | High | cancel_recovery requires both WebAuthn signature AND fresh seed-knowledge proof; cap of 2 cancels per initiation; 24h cooldown between cancels; cancel events emitted to user notification channel. |
| 12 | TTL archival race — pending-rotation state archived during 30-day window | Medium | Critical | Per-account recovery deposit at enrollment covers ~40 days of TTL extension; complete_recovery fails-closed if rent exhausted; RestoreFootprint ordering specified (restored state cannot retroactively re-open a completed/cancelled recovery). |
| 13 | Pubkey encoding malleability | Medium | Critical | In-circuit on-curve check on P-256 pubkey; canonical-limb decomposition (hi*2^128 + lo < secp256r1_modulus); A1 unit tests cover non-canonical encodings as adversarial inputs. |
| 14 | Pre-enrollment squatting — attacker phishes mnemonic before user enrolls, registers commitment first | Low | High | Enrollment binds commitment to account_id; an unenrolled C-address has no commitment to attack; user education at enrollment emphasizes sequential ordering (create account → write down phrase → register commitment, all in one flow). |
| 15 | VK-upgrade UI coercion attack | Medium | High | "Required VK refresh" prompts disallowed in integrator's-guide UX standard; VK upgrades surface as opt-in only with 14-day visibility; 2 independent on-chain monitors required to publish VKUpgradeProposed alerts before any wallet defaults to opt-in. |
| 16 | bb.js supply-chain attack | Medium | Critical | SRI hash for the bb.js bundle pinned in the wallet HTML; reproducible-build verification published in A5; npm registry compromise mitigated by vendoring the WASM artifact. |
| 17 | Recovery-card QR exfiltration | Medium | High | Recovery card contains C-address only, NEVER the seed. Seed lives on a separate paper artifact never digitized. A5 acceptance criterion for the export tooling. |
| 18 | Recovery-deposit griefing | Low | Medium | Per-account recovery initiation rate-limit: max 3 initiate_recovery per 90-day rolling window. |
| 19 | mysoroban.xyz origin compromise | Low | Critical | Acknowledged as a top-of-stack risk that SRI cannot defend against. Mitigations in scope: DNSSEC, COOP/COEP, strict CSP, signed-loader bootstrap. Out of scope (post-grant): native-app option + hardware-wallet integration path; user education that recovery from a compromised origin requires waiting + filing a SmartAccount disclosure. Risk explicitly enumerated so SDF and integrators can plan defense-in-depth. |
| 20 | Kill-switch DoS | Low | High | First pause is 1-of-5 for 7 days; second pause within 30 days requires 4-of-5. One compromised signer cannot indefinitely block emergency VK rotation. |
| 21 | VK upgrade governance bias | Low | High | SDF + Stellar Foundation external signers treated as one effective vote for collusion analysis only; the on-chain rule is 3-of-5 with the diversified-quorum predicate. Every accepted quorum requires at least one outside-Group-A signature, so SDF+SF collusion still requires OZ or community consent. Documented in A2 governance design + grant agreement. |

## 10. Why bundle, expanded

The engineering case for one grant over two:

- One verifier crate (ultrahonk-soroban-verifier) serves both pillars.

- One browser proving harness (bb.js + WebWorker + /recover/ route).

- One Poseidon2 parameter set, domain-separated per use, audited once.

- One VK registry + one governance mechanism.

- One audit RFP covering circuits + contracts + integration.

We deliver a cross-repo dependency graph as the first artifact of A1.

Bundling saves engineering time only because Track A and Track B share a substrate. They do not share business logic, end-users, regulatory posture, or success criteria. Disbursement is therefore independent (§8).

## 11. Pillar 2 compliance gates

Track B funds gated on the following deliverables from the neftwerk team. Reviewed by a named SDF compliance reviewer (designated at grant signing).

| Gate | Deliverable | Track B effect |
| --- | --- | --- |
| C1 | MSB / NY VTL / EU VASP / MiCA classification opinions for ARTS-1 primary issuance | B1 held until C1 in SDF reviewer's hands |
| C2 | On-chain freeze function pursuant to documented legal process. Implemented as B6 acceptance. | Blocking for B6 |
| C3 | Howey opinion for single-edition ARTS-1 tokens, including treatment of enforced royalties; explicit no-fractionalization covenant | Blocking for B6, reviewed by SDF reviewer |
| C4 | Geographic scoping plan: Reg-S-style geofence during grant period; KYC threshold for secondary transfers above $X | Blocking for B6 |
| C5 | Estate-planning disclosure flow at enrollment | Blocking for B7 |

If any gate is not met by week 9, Track B is paused; Track A continues unaffected.

Branding: SDF logo and "funded by SDF" language do not appear on Pillar 2 marketing pages until C1–C4 are implemented.

## 12. Universality argument

The recovery circuit is a key-rotation primitive any Soroban Smart Account can adopt; neftwerk is the second consumer, not the only one. Concrete future consumers:

- Custody wallets needing non-custodial paper-mnemonic recovery

- RWA issuers (real estate, supply-chain, carbon credits) needing ownership privacy with provable transfer history

- Compliance-sensitive institutions wanting counterparty privacy without surrendering provability

A6 deliverable includes a one-page integrator's guide: the minimal interface a Soroban contract has to implement to consume the ZK recovery primitive. At least one external wallet integrator's signed integration agreement is required at A6.

## 12.5. Roadmap: fast-recovery path (post-grant)

The 30-day timelock is incompatible with high-velocity collector use cases (insurance renewals, museum loans, estate updates). Post-grant deliverable: a Shamir-style fast-recovery path with the threshold scheme (collector + 1-of-{gallery, Neftwerk}) — collector's share is mandatory, foreclosing institutional-only recovery. Additive on top of the current recovery primitive; no breaking change.

## 13. References / repo file map

### g2c

- g2c/APPLICATION.md

- g2c/ARCHITECTURE.md

- g2c/contracts/smart-account/src/contract.rs

- g2c/contracts/factory/src/contract.rs

- g2c/contracts/webauthn-verifier/src/contract.rs

### ZK substrate / proof-of-concept

- zk/rs-soroban-ultrahonk/README.md

- zk/rs-soroban-ultrahonk/ultrahonk-soroban-verifier/src/

- zk/rs-soroban-ultrahonk/<nullifier_set_primitive>/ (renamed before kickoff)

- zk/soroban-zk-demo/README.md and test_e2e.sh

- zk/soroban-zk-demo/circuits/ownership_proof/src/main.nr (to be brought into spec at A0)

### Neftwerk

- zk/neftwerk/Neftwerk_White_Paper_Summary.md

- zk/neftwerk/Neftwerk_Creation_Privacy_Flow.md

- zk/neftwerk/Neftwerk_Sale_Privacy_Flow.md

- zk/neftwerk/milestones.md

- zk/neftwerk/review-technical.md

- zk/neftwerk/review-legal.md

- zk/neftwerk/review-gallery.md

### External

- Noir: https://noir-lang.org/

- Barretenberg / UltraHonk: https://github.com/AztecProtocol/aztec-packages

- noir-bigcurve, noir_ecdsa: noir-lang org

- OpenZeppelin Stellar Contracts: stellar-contracts-OZ/

## Appendix A — Cryptographic parameters

### A.1 — Encoding spec

All Field-bound inputs to Poseidon2 follow these rules:

- 65-byte uncompressed P-256 pubkey (0x04 ‖ x ‖ y): split into 5 limbs of ≤128 bits via big-endian decomposition. Order: (prefix_byte, x_hi, x_lo, y_hi, y_lo). Each limb range-checked < 2^128 in-circuit. Composition check: prefix == 0x04 and x = x_hi * 2^128 + x_lo and y = y_hi * 2^128 + y_lo and (x, y) lies on secp256r1.

- account_id (Stellar StrKey / BytesN<32>): 32 bytes interpreted as 2 BN254 field elements (hi, lo) via 16-byte big-endian split. Range-checked.

- network_passphrase (variable string): SHA-256 hashed, then encoded as 2 BN254 field elements via the same 16-byte split.

- contract_addr (Stellar contract address / BytesN<32>): same as account_id.

- nonce: 8 bytes BE → 1 Field.

- timelock_duration: 4 bytes BE seconds → 1 Field.

- token_id: 32 bytes → 2 Field elements (16-byte split).

### A.2 — Domain separators

- domain_sep_commitment = Poseidon2("g2c-recovery-v1-commitment")

- domain_sep_recovery = Poseidon2("g2c-recovery-v1-auth-hash")

- domain_sep_cancel = Poseidon2("g2c-recovery-v1-cancel-hash")

- domain_sep_arts1_mint = Poseidon2("arts1-mint-v1")

- domain_sep_arts1_own = Poseidon2("arts1-ownership-v1")

- domain_sep_arts1_rec = Poseidon2("arts1-recovery-v1")

- domain_sep_nullifier = Poseidon2("nullifier-set-primitive-v1")

All domain separators are passed as the first input element of every Poseidon2 call. The Aztec Poseidon2 sponge is multi-input-collision-resistant under standard assumptions.

### A.3 — Other parameters

- Curve. BN254 (alt_bn128), 254-bit prime field. ~100-bit pairing security.

- Migration plan. VK registry supports parallel BLS12-381 verifier deployment without disrupting BN254-pinned accounts. BLS12-381 prototype committed as post-grant deliverable; full migration estimated 2027–2028.

- HKDF. SHA-256 PRF; ikm = BIP-39 seed, salt = network_passphrase (raw string), info = "g2c-recovery-v1" ‖ account_id (33 bytes), output length = 32 bytes, then reduced modulo BN254 scalar order. Bias from naive mod q is ~2⁻²⁵² — acceptable.

- Proof system. UltraHonk via Barretenberg; Fiat-Shamir, Sumcheck, Shplonk.

- Sizes (measured). VK ≈ 1.9 KB, proof ≈ 3.7 KB.

- G2 SRS. Aztec's powers-of-tau ceremony output, hardcoded in ec.rs:7-27. SDF acceptance is a discussion point in the 30-minute review.

## Appendix B — Prior art

- Semaphore-style group-membership patterns. Source of the commit-then-prove + nullifier-set pattern.

- Aztec Protocol. UltraHonk's home.

- OpenZeppelin Stellar SmartAccount. Verifier-per-signer + Policy pattern.

- BIP-39. Mnemonic format for offline seed storage.

- Argent / Safe wallet recovery. Reference for timelock + guardian patterns; we deliberately use cryptographic guardianship instead of social.

End of appendix. See SDF_PROPOSAL_ONE_PAGER.md for the executive summary.